## Sheet1
Sample Workplan ¦ Love Your Heart Post-Event to Next Year's Event
Categories:
Communications/Marketing
Data/IT
Partner and Volunteer Management
Other
| Week of | Deliverable | Targeted Due Date | Lead | Status (Pending/Complete)
|  | Schedule Recognition Event with speakers; Secure Location | 2018-03-02
| 2018-02-26 | Produce draft program for Recognition Event/identify potential speakers | 2018-03-02
|  | Tactical Team post-event debrief/ review of workplan | 2018-03-01
February |  | Sketch out wireframe of LYH annual report | 2018-03-02
(Event Month) |  | Outreach to sites to collect remaining data (including comparing site map/list to site data collected to identify pending data) | 2018-03-02
|  | Draft 1 (layout) of report produced and shared with Executives for review | 2018-03-05
| 2018-03-05 | Draft save-the-date for Recognition Event + generate RSVP link | 2018-03-09
|  | Generate list of Love Your Heart Partners for invitation to recognition event, as well as annual report and website | 2018-03-09
|  | Identify LYH personal stories from screening sites + any quotes | 2018-03-09
March |  | Data input and QA continues (i.e. confirm no duplicate data, etc.) | 2018-03-09
(T-11 Months) |  | All LYH photos saved/uploaded | 2018-03-09
| 2018-03-12 | Draft 2 of layout of report produced and shared with Executives for review for feedback with one week review period | 2018-03-12
|  | Send Save-the-Date to LYH Partners | 2018-03-14
|  | QA'd Data sent to data team for review | 2018-03-16
| 2018-03-19 | Produce tables and figures and any key data findings for report + data slide show | 2018-03-23
|  | Feedback on Draft 2 of report recieved | 2018-03-19
| 2018-03-26 | Final Data Tables and Figures integrated into report, Integrate Feedback on report received, generate Draft 3 of report | 2018-03-30
| 2018-04-02 | Draft 3 of report shared with Executives w 2 week review period | 2018-04-02
April | 2018-04-09
(T-10 Months) |  | Produce overview + data slides for Recognition Event for speakers' review | 2018-04-13
| 2018-04-16 | Produce photo slide deck for Recognition Event | 2018-04-20
| 2018-04-16 | Final feedback integrated into report and toolkit | 2018-04-20
| 2018-04-23 | Produce Final Report and confirm no further changes | 2018-04-25
| 2018-04-30 | Print Report + Recognition Event programs | 2018-05-04
|  | Gather any additional supplies needed for Recognition Event (tablecloths, etc.) | 2018-05-04
| 2018-05-07 | Recognition Event Takes Place--Day-of support (room setup, etc.) | TBD
|  | Post report on loveyourheartsd.org; send out via eBlast to partners | TBD
May | 2018-05-14
(T-9 months) | 2018-05-21
2018-05-28
| 2018-06-04 | Identify/confirm members and leads for Love Your Heart Steering Committee and Tactical Team | 2018-06-08
June | 2018-06-11 | Confirm Love Your Heart event date/any conflicts or contingencies | 2018-06-22
(T-8 months) | 2018-06-18 | Update partner recruitment presentation | 2018-06-29
2018-06-25
| 2018-07-02 | Commence recruitment presentations to potential partners | 2018-10-31
July | 2018-07-09 | Review previous year's screening data to identify which screening sites should carry over to new year, which might be combined/condensed, and new sites that may be added | 2018-07-23
(T-7 months) | 2018-07-16 | Identify potential key educational messages or themes | 2018-07-31
2018-07-23
| 2018-07-30 | Develop updated marketing and communications plan/schedule | 2018-08-15
| 2018-08-06 | Develop updated data capture methods (registration page, mobile app in English and Spanish, aggregate response app, paper forms) | 2018-08-31
| 2018-08-13 | Refresh educational and promotional materials as needed including social media playbook | 2018-08-31
August | 2018-08-20
(T-6 months) | 2018-08-27
| 2018-09-03 | Targeted early volunteer group recruitment (nursing programs, graduate programs, etc.)
September | 2018-09-10
(T-5 months) | 2018-09-17
2018-09-24
| 2018-10-01 | Volunteer registration opens
Site registration opens
|  | Volunteer and site recruitment | 2019-01-15
October | 2018-10-08
(T-4 months) | 2018-10-15 | Schedule media kick-off event | 2018-11-01
2018-10-22
2018-10-29
| 2018-11-05 | Resource matching (continuous) | 2019-01-15
2018-11-12
November | 2018-11-19 | Initial Outreach to media partners regarding promotional ideas | 2019-01-07
(T-3 months) | 2018-11-26
| 2018-12-03 | Determine quantities of print materials and give aways; include American Heart Association in discussion | 2018-12-17
December | 2018-12-10 | Schedule volunteer and site coordinator trainings | 2018-12-17
(T-2 months) | 2018-12-17 | Update volunteer and site coordinator training materials | 2019-01-14
| 2018-12-24 | Print LYH hard copy materials and giveaways | 2019-01-07
| 2019-01-07 | Script, scout and film Love Your Heart PSAs | 2019-02-01
|  | Distribute hard copies of hard copy materials and giveaways to Regional Leads | 2019-01-14
January | 2019-01-14 | Regions bundle hard copy materials and giveaways for sites | 2019-01-21
(T-1 months) | 2019-01-21 | Identify sites for social and traditional media coverage | 2019-01-28
|  | Conduct train the trainer trainings | 2019-01-28
| 2019-01-28 | Conduct site and volunteer trainings | 2019-02-04
| 2019-02-04 | Love Your Heart media kickoff event | 2019-02-11
2019-02-11
February | 2019-02-11 | Event Day! | 2019-02-14
Event Month | 2019-02-18 | Data gathering and QA
|  | "Quick-Take" feedback from sites | 2019-02-25
| 2019-02-25 | Initial headcount confirmed | 2019-02-25